## Slide 1: Idaho Cleanup Project Update Leadership in Nuclear Energy Commission
Jack Zimmerman
Deputy Manager
Idaho Cleanup Project
Oct. 4, 2017

## Slide 2: Stored Transuranic Waste Status
As noted in our April presentation, our contractor completed retrieval of all stored transuranic waste earlier this year.
At our treatment facility, significant upgrades were completed including new Brokks, all boxlines are operational and we have increased treatment facility shifts from 12/7 to 24/7.
Fluor is about 300 cubic meters behind the contract schedule in treating contact-handled waste. The amount of direct feed waste is limited, and we are treating more small quantity, difficult-to-treat waste – therefore we are getting less production for the same effort.
New Brokk 400 operating in the South Box Line
Excavator dumps sludge drum into tray at ARP V facility

## Slide 3: New Capabilities for CH-TRU Processing
Accelerated Retrieval Project (ARP) retrieval enclosures are used primarily for exhumation of targeted buried waste.
The new ARP IX facility, however, is also being considered for “roaster oxide” processing prior to beginning its buried waste exhumation mission.
“Roaster oxides” are uranium oxide metal that are pyrophoric – they can ignite in the presence of air. Some of the transuranic waste stored here contains roaster oxides, which require processing before they can be packaged for shipment to WIPP.
The Accelerated Retrieval Project IX facility (left and above), the last buried waste retrieval enclosure, was completed this summer.

## Slide 4: Shipping and Certification
AMWTP Certified Program:
Starting the week of Sept. 18, Idaho Cleanup Project shipments of transuranic waste to WIPP increased from two to four per week.
  Completed 46 shipments to date since shipping resumed April 6, 2017.
  We have shipped about 54,000 cubic meters of transuranic and mixed low-level waste from the original 65,000 cubic meter Settlement Agreement inventory to out-of-state disposal facilities.
The next AMWTP Recertification Audit will be in early December, 2017
  Expect to demonstrate complete process now that the Basis of Knowledge has been released.
  The Generator Site Technical Review is complete.

## Slide 5: Settlement Agreement TRU Production Status

## Slide 6
Buried Transuranic Waste
Drum exhumation from Accelerated Retrieval Project VIII.
Status of Targeted Waste Exhumation:
Completed exhumation of 4.71 acres of buried waste as of Oct. 1, 2017. Regulatory goal: 5.69 acres by 2023.
As noted earlier, the final retrieval enclosure facility (ARP IX) was completed earlier this summer. Exhumation will begin there next year.
Over 7,500 cubic meters of targeted waste has been exhumed to date.
Project is expected to be completed about two years ahead of regulatory milestone.

## Slide 7: Buried Waste Exhumation Work-off Chart
Notes: Still tracking about 2 years ahead of enforceable milestone.

## Slide 8
Liquid Waste Treatment Background
There are about 900,000 gallons of liquid radioactive waste stored safely in three stainless steel underground tanks at the Idaho Nuclear Technology and Engineering Center.
The Integrated Waste Treatment Unit (IWTU) was constructed to treat the waste, but design problems have prevented the beginning of waste treatment.

## Slide 9: Approach to Address Remaining Issues
Fluor Idaho has established a systematic, mechanistic based approach involving 4 phases to address issues with the IWTU.
A team of specialists was assembled to work with IWTU staff, including experts in fluidized bed technology that have solved similar problems in industry.
Flour established a Technical Review Group consisting of subject matter experts from National Labs, industry and academia to provide input and advice.
Fluor has enlisted the Particulate Solid Research Institute (PSRI) to assist in the testing and evaluation of fluidized bed improvements.
Small Scale Tests,
Engineering Evaluations
and Modeling
Pilot and IWTU Test Runs
Rad Ops
Confirm Fixes
In Progress
Complete
Small Scale Tests,
Engineering Evaluations
and Modeling

## Slide 10: Summary Status of the 5 Main Issues
Issue: Formation of Sandcastles
Status: Sandcastle formation mechanisms understood. Implementing changes in IWTU.
Issue: Wall Scaling
Status: Impact has been reduced. Improved understanding of wall scale formation and control mechanisms.
Issue: DMR Instabilities
Status: Mechanisms understood. DMR instabilities are due to sandcastles.
Resolved
Understood
Understood
Impact Reduced
Resolved
Issue: Ring Header Damage
Status: DMR access approach resolved. Manway installation completed. Will replace damaged ring with Double Plenum and Cone configuration.
Issue: Auger-Grinder Failure
Status: Issues were successfully addressed in the March 2017 run.

## Slide 11: Issue: Formation of Sandcastles
  Issue
  In areas of insufficient fluidization in the Denitration Mineralization Reformer (DMR), particles can settle or agglomerate and disrupt gas flow and mixing, resulting in temperature variations in the DMR, formation of sandcastles, further de-fluidization and other operational impacts.
  Cause
  Insufficient fluidization and mixing.
  Agglomeration of cohesive or sticky particles due to slow or incomplete waste feed conversion reactions.
  Approach to Resolve
  Extensive work by INL to understand reaction kinetics.
  Modeling by National Energy Technology Laboratory (NETL) to understand fluid dynamics and mixing in the DMR.
  Bench-scale, pilot plant, and cold flow testing to investigate sandcastle formation and mitigation.
  Status
  Sandcastle formation mechanisms understood.
  Replacing Fluidizing Gas Rails and Ringheader with Double Plenum and Cone
  configuration.
Modeling showing area of weak fluidization (red circle) where sandcastles form.

## Slide 12: DMR Reconfiguration
Double Plenum and Cone Configuration
Eliminates stagnant (defluidized)
areas of the Denitration and
Mineralization (DMR) bed.
Reduces in-bed obstructions.
Provides flexibility in fluidizing
gas and steam composition in
Upper and Lower plenums.
Consistent with state of the art.

## Slide 13: Spent Nuclear Fuel Disposition Project
Looking down from the overhead cranes into the pools of CPP-666
Completed ten EBR-II spent fuel transfers out of wet storage, more than the six planned.
Completed 24 of 24 planned Advanced Test Reactor (ATR) transfers out of wet storage.
We are currently on target to meet the 2023 Settlement Agreement Milestone to move all spent nuclear fuel to dry storage.
High-Load Charger used to transfer ATR SNF
Notes:   Removed item discussing transfer of TRIGA fuel from 603 to MFC. It is an NE research program and doesn’t really reflect on the EM spent fuel mission.

## Slide 14: Summary of Accomplishments in FY17
Fluor completed retrieval of remaining stored transuranic waste.
Exhumed .40 acre of targeted buried waste.
Shipments of transuranic waste resumed to the Waste Isolation Pilot Plant, completing 46 since April, 2017.
Completed 45 transfers of spent nuclear fuel from wet to dry.
Resolved important issues related to start-up of the Integrated Waste Treatment Unit (IWTU).
On the road to resolving the critical issue of fluidization in the IWTU main processing cell.